## Work packages Backlog
The effect and the key performance indicators using blemish on the high resolution lidar imaging sensor
PROJECT TITLE |  | The effect and the key performance indicators using blemish on the high resolution lidar imaging sensor
PROJECT DESCRIPTION |  | At the R&D Lidar department at Valeo, we are developing the next generation of LIDARs which has high resolution point cloud in both vertical and horizontal field of view with state of the art perception stack. The project aims to find the defected imager sections by emulating laser shooting sequence from an external light source. This helps to increase the quality of the LIDAR production at the end of line process. At the end of the project, these goals to be achieved: 1. Understanding the LIDAR sensor and principle. 2. Understanding the active and passive images in the camera domain. 3. Identification of different light source including intensity to perform blemish measurement. 4. Identification of intensity to perform blemish measurement. 5. Automation of the image processing for particle estimation. 6. Definition of the quality criteria for successful calibration. 7. Comprehension of the industrialization and automation concepts. 8. Validation and verification concepts comprehension. 9. Agile and scrum methodologies comprehension. 10. Clean coding. 11. Software and system architecture concepts. 12. Depth knowledge in algorithms including machine learning algorithms. 13. Verification and validation of such algorithms within the research scope. 12. Documentation. 13. Paper Submission
Supervisor |  | Michael AECKERLE
Technical Supervisors |  | Sarath Manchala, Urs ZYWIETZ, Ahmed YOUSIF
CURRENT CALENDAR WEEK |  | 46
CURRENT DATE |  | 2022-11-16
START DATE |  | 2022-11-01
Potential Conferences
NUMBER | TASK TITLE | Dependency | START DATE | DUE DATE | DURATION [Day] | Responsible | % of completion
Comments
1 | Simulation Tools Comprehension | [5 empty] | #DIV/0!
1.1 | CarMaker Understanding | - | 2022-11-01 | 2022-11-08 | 7 | Student |  | Full comprehension of the automotive simulation concept
1.2 | Scenario Creation | 1.1 | 2022-11-04 | 2022-11-11 | 7 | Student |  | Scenario creation includes traffic, objects and lanes
1.3 | ADAS Systems Understanding | 1.2 | 2022-11-12 | 2022-11-19 | 7 | Student |  | Full comprehension of autonomous driving systems and all the levels from L1 to L5
1.4 | Scenario Creation with ADAS Functions | 1.3 | 2022-11-12 | 2022-11-19 | 7 | Student |  | Ability to create different scenarios for testing and validation of ADAS systems
1.5 | High Fidelity Lidar Sensor Model Overview and Comprehension | 1.3 | 2022-11-12 | 2022-11-19 | 7 | Student |  | Comprehend the basics on the simulation sensor model including also LIDAR properties and artifacts
2 | Literature Review | [5 empty] | #DIV/0!
2.1 | Research Camear based Blemish Concept, applicablity to lidar | - | 2022-11-20 | 2022-12-11 | 21 | Student |  | Research depth image and image processing algorithm in the current state of art from scientific papers and conferences
2.2 | Definition active and passive imaging concept | 2.1 | 2022-12-12 | 2022-12-19 | 7 | Student |  | Define the algorithms to be developed based on the research
2.3 | Research state of the art algorithms | - | 2022-11-20 | 2022-12-11 | 21 | Student |  | Research state of the art algorithms on Lidar point cloud in the current state of art from scientific papers and conferences
2.4 | Definition of serial production concept | 2.3 | 2022-12-20 | 2022-12-27 | 7 | Student |  | Define the algorithms to be developed based on the research
3 | Algorithm Development | [5 empty] | #DIV/0!
3.1 | Definition and design of algorithm | - | 2022-12-28 | 2023-02-26 | 60 | Student |  | Development of defined algorithms on C++ preferably
3.2 | Benchmarking the lidar point cloud algorithms | 3.3 | 2023-02-27 | 2023-03-13 | 14 | Student |  | Benchamrk the performance of the developed algorithms
3.3 | Validation and Verification of the algorithms | 3.3 | 2023-03-14 | 2023-03-28 | 14 | Student |  | Validation and verification of the algorithms by defined test cases
3.1 | Specification of Limits and thresholds | 3.3 | 2023-03-29 | 2023-04-12 | 14 | Student |  | Benchamrk the performance of the developed algorithms
4 | Test Case: Sensor Technology Implementation | [5 empty] | #DIV/0!
4.1 | Integrating the algorithms to SW | 3 | #REF! | #REF! | #REF! | Student
4.2 | Verification and validation of the integration | 4.1 | #REF! | #REF! | #REF! | Student |  | Validation and verification of the algorithms by defined test cases on the simulation tool
4.3 | Benchmarking the algorithms and Serial Production concept | 4.1 | #REF! | #REF! | #REF! | Student |  | Benchamrk the performance of the developed algorithms within the tool
5 | Documentation | [5 empty] | #DIV/0!
5.1 | Documentation of the Introduction | 1 | 2022-11-01 | 2022-11-19 | 18 | Student |  | Introduction shall include problem statement, mission, vision and outcome
5.2 | Documentation of the literature review | 2 | 2022-11-20 | 2022-12-27 | 37 | Student |  | Literature review in the market and research paper on simulation, ADAS and standards
5.3 | Documentation of the system definition | 2 | 2022-11-20 | 2022-12-27 | 37 | Student |  | Development explanation documentation
5.4 | Documentation of the system design | 2 | 2022-12-28 | #REF! | #REF! | Student |  | Development explanation documentation
5.4.1 | Documentation of the system/ software architecture (Statemachine, Sequence diagrams) | 3 | 2023-02-27 | #REF! | #REF! | Student |  | Development explanation documentation
5.5 | Documentation of the implementation, Serial production concept | 3 | 2023-02-27 | #REF! | #REF! | Student |  | Development explanation documentation
5.6 | Documentation of the Usecase, imits, test results | 4 | #REF! | #REF! | #REF! | Student |  | Documentation of the test cases defined to test the development of the solution
5.7 | Documentation of future improvement | 4 | #REF! | #REF! | #REF! | Student |  | Documentation on the gaps, problems faced, future improvement and effort estimations
5.8 | Review of Documentation | 5.7 | 2022-12-28 | #REF! | #REF! | Engineer/ Manager |  | Review the document by validation engineers, simulation engineers and direct manager of the student
5.8 | Presentation Preperation | - | #REF! | #REF! | #REF! | Student |  | Presentation preperation for the defence
Formulas:
START DATE = [START DATE, row above]+3
START DATE = [DUE DATE, row above]+1
DUE DATE = [START DATE]+7

## SCRUM
Calendar Week |  |  | 46
Weekday |  |  | Wednesday
Date and Time |  |  | 2022-11-16
Date | Team Member | What I've done yesterday? | What I'll do today? | What impeds me?
2022-11-01 | Kishore SINGH
2022-11-02
2022-11-03
2022-11-04
2022-11-05
2022-11-06
2022-11-07
2022-11-08
2022-11-09
2022-11-10
2022-11-11
2022-11-12
2022-11-13
2022-11-14
2022-11-15
2022-11-16
2022-11-17
2022-11-18
2022-11-19
2022-11-20
2022-11-21
2022-11-22
2022-11-23
2022-11-24
2022-11-25
2022-11-26
2022-11-27
2022-11-28
2022-11-29
2022-11-30
2022-12-01
2022-12-02
2022-12-03
2022-12-04
2022-12-05
2022-12-06
2022-12-07
2022-12-08
2022-12-09
2022-12-10
2022-12-11
2022-12-12
2022-12-13
2022-12-14
2022-12-15
2022-12-16
2022-12-17
2022-12-18
2022-12-19
2022-12-20
2022-12-21
2022-12-22
2022-12-23
2022-12-24
2022-12-25
2022-12-26
2022-12-27
2022-12-28
2022-12-29
2022-12-30
2022-12-31
2023-01-01
2023-01-02
2023-01-03
2023-01-04
2023-01-05
2023-01-06
2023-01-07
2023-01-08
2023-01-09
2023-01-10
2023-01-11
2023-01-12
2023-01-13
2023-01-14
2023-01-15
2023-01-16
2023-01-17
2023-01-18
2023-01-19
2023-01-20
2023-01-21
2023-01-22
2023-01-23
2023-01-24
2023-01-25
2023-01-26
2023-01-27
2023-01-28
2023-01-29
2023-01-30
2023-01-31
2023-02-01
2023-02-02
2023-02-03
2023-02-04
2023-02-05
2023-02-06
2023-02-07
2023-02-08
2023-02-09
2023-02-10
2023-02-11
2023-02-12
2023-02-13
2023-02-14
2023-02-15
2023-02-16
2023-02-17
2023-02-18
2023-02-19
2023-02-20
2023-02-21
2023-02-22
2023-02-23
2023-02-24
2023-02-25
2023-02-26
2023-02-27
2023-02-28
2023-03-01
2023-03-02
2023-03-03
2023-03-04
2023-03-05
2023-03-06
2023-03-07
2023-03-08
2023-03-09
2023-03-10
2023-03-11
2023-03-12
2023-03-13
2023-03-14
2023-03-15
2023-03-16
2023-03-17
2023-03-18
2023-03-19
2023-03-20
2023-03-21
2023-03-22
2023-03-23
2023-03-24
2023-03-25
2023-03-26
2023-03-27
2023-03-28
2023-03-29
2023-03-30
2023-03-31
2023-04-01
2023-04-02
2023-04-03
2023-04-04
2023-04-05
2023-04-06
2023-04-07
2023-04-08
2023-04-09
2023-04-10
2023-04-11
2023-04-12
2023-04-13
2023-04-14
2023-04-15
2023-04-16
2023-04-17
2023-04-18
2023-04-19
2023-04-20
2023-04-21
2023-04-22
2023-04-23
2023-04-24
2023-04-25
2023-04-26
2023-04-27
2023-04-28
2023-04-29
2023-04-30
2023-05-01
2023-05-02
2023-05-03
2023-05-04
2023-05-05
2023-05-06
2023-05-07
2023-05-08
2023-05-09
2023-05-10
2023-05-11
2023-05-12
2023-05-13
2023-05-14
2023-05-15
2023-05-16
2023-05-17
2023-05-18
2023-05-19
2023-05-20
2023-05-21
2023-05-22
2023-05-23
2023-05-24
2023-05-25
2023-05-26
2023-05-27
2023-05-28
2023-05-29
2023-05-30
2023-05-31
Formulas:
Date = [Date, row above]+1

## Timeline
# | TASK TITLE | CW44 | [5 empty] | CW45 | [6 empty] | CW46 | [6 empty] | CW47 | [6 empty] | CW48 | [6 empty] | CW49 | [6 empty] | CW50 | [6 empty] | CW51 | [6 empty] | CW52 | [6 empty] | CW01 | [6 empty] | CW02 | [6 empty] | CW03 | [6 empty] | CW04 | [6 empty] | CW05 | [6 empty] | CW06 | [6 empty] | CW07 | [6 empty] | CW08 | [6 empty] | CW09 | [6 empty] | CW10 | [6 empty] | CW11 | [6 empty] | CW12 | [6 empty] | CW13 | [6 empty] | CW14 | [6 empty] | CW15 | [6 empty] | CW16 | [6 empty] | CW17
|  | November | [29 empty] | December | [30 empty] | January | [30 empty] | February | [27 empty] | March | [30 empty] | April
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | Simulation Tools Comprehension
1.1 | CarMaker Understanding
1.2 | Scenario Creation
1.3 | ADAS Systems Understanding
1.4 | Scenario Creation with ADAS Functions
1.5 | High Fidelity Lidar Sensor Model Overview and Comprehension
2 | Literature Review
2.1 | Research depth image and image processing algorithm in the current state of art
2.2 | Definition of the depth image algorithm to be used in this research on point cloud
2.3 | Research state of the art algorithms on Lidar point cloud
2.4 | Definition of the point cloud algorithm to be used in this research on point cloud
3 | Algorithm Development
3.1 | Implementation of the depth image algorithms
3.2 | Benchmarking the depth image algorithms
3.3 | Implementation of the lidar point cloud algorithms
3.4 | Benchmarking the lidar point cloud algorithms
3.5 | Validation and Verification of the algorithms
4 | Test Case: Sensor Technology Implementation
4.1 | Integrating the algorithms to a simulation tool
4.2 | Verification and validation of the integration
4.3 | Benchmarking the algorithms within the simulation tool
5 | Documentation
5.1 | Documentation of the Introduction
5.2 | Documentation of the literature review
5.3 | Documentation of the system and software definition
5.3.1 | Documentation of the system/ software requirements
5.3.2 | Documentation of the system/ software model
5.3.3 | Documentation of the system/ software sequence diagram
5.4 | Documentation of the system design
5.4.1 | Documentation of the system/ software architecture
5.4.2 | Documentation of the system/ software component specification
5.4.3 | Documentation of the interface definitions
5.5 | Documentation of the implementation
5.6 | Documentation of the test case
5.7 | Documentation of future improvement
5.8 | Review of Documentation
5.8 | Presentation Preperation